NexGen Pharma QMS

Sprint Plan & Development Backlog

v0.6 → v1.0  |  Praverse Tech Pvt. Ltd.  |  May 2026

# Sprint Overview

This document defines the full sprint-by-sprint execution plan from v0.6 to v1.0. Each sprint is 2 weeks. Story points follow Fibonacci scale (1, 2, 3, 5, 8, 13). Team velocity assumed at 40 SP/sprint (2 backend, 2 frontend engineers + 1 QA).

| Version | Sprints | Duration | Focus | Exit Criteria |
| --- | --- | --- | --- | --- |
| v0.6 | S1–S4 | 8 weeks | Audit Mgmt + Audit Trail Export + CAPA Effectiveness | Audit module QA-approved, PDF export working |
| v0.7 | S5–S8 | 8 weeks | Complaint Handling + OOS/OOT + NC Management | All Phase 1b modules with full workflow + e-sig |
| v0.8 | S9–S12 | 8 weeks | Risk Management + Supplier Quality Management | Risk matrix live, ASL approved workflow complete |
| v0.9 | S13–S18 | 12 weeks | Batch Records (eBMR/eBPR) + Sample Management | End-to-end batch release + COA generation |
| v1.0 | S19–S24 | 12 weeks | Analytics, APQR, 21 CFR Part 11 audit, Validation docs | System validation package complete, pen test passed |

## SPRINT 1 (v0.6) — Audit Module: Backend Foundation

Sprint Goal: Set up audits/ Django app with core models, serializers, permissions, and basic CRUD API.

Total story points: 39

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-001 | Create audits/ Django app with Audit, Finding, AuditPlan models | 8 | Backend | In Progress |
| BE-002 | Implement AuditSerializer, AuditViewSet with RBAC permissions | 5 | Backend | To Do |
| BE-003 | Create Finding model with severity choices and CAPA FK | 5 | Backend | To Do |
| BE-004 | Add workflow transitions: Draft→Active→Completed→Closed | 5 | Backend | To Do |
| BE-005 | Write unit tests for audit workflow (pytest) | 3 | Backend | To Do |
| FE-001 | Scaffold /audits route and AuditList page with DataTable | 5 | Frontend | To Do |
| FE-002 | AuditForm component: type, scope, dates, lead auditor fields | 5 | Frontend | To Do |
| QA-001 | Write test plan for Audit Management module | 3 | QA | To Do |

## SPRINT 2 (v0.6) — Audit Module: Findings + CAPA Link

Sprint Goal: Complete finding management, finding-to-CAPA linking, and audit report generation.

Total story points: 39

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-006 | FindingViewSet with evidence file upload (FileField) | 5 | Backend | To Do |
| BE-007 | AuditResponse model — auditee response tracking with deadline | 5 | Backend | To Do |
| BE-008 | Auto-generate CAPA record on critical finding submission | 5 | Backend | To Do |
| BE-009 | Audit report endpoint — serialize full audit + findings to JSON | 5 | Backend | To Do |
| FE-003 | FindingForm with severity badges and evidence file uploader | 5 | Frontend | To Do |
| FE-004 | WorkflowTimeline component for audit status history | 3 | Frontend | To Do |
| FE-005 | Audit detail page: summary + findings list + response panel | 8 | Frontend | To Do |
| QA-002 | Execute finding creation + CAPA linking test cases | 3 | QA | To Do |

## SPRINT 3 (v0.6) — Audit Trail Export + CAPA Effectiveness

Sprint Goal: Deliver audit trail PDF/Excel export and CAPA effectiveness verification workflow.

Total story points: 45

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-010 | AuditTrailExport endpoint — paginated field-level changelog | 8 | Backend | To Do |
| BE-011 | PDF export of audit trail using reportlab/weasyprint | 8 | Backend | To Do |
| BE-012 | Excel export using openpyxl for audit trail | 3 | Backend | To Do |
| BE-013 | EffectivenessCheck model — criteria, due date, result, status | 5 | Backend | To Do |
| BE-014 | CAPA state: add 'effectiveness_pending' and 'closed' gated by EffectivenessCheck | 5 | Backend | To Do |
| FE-006 | Audit Trail Viewer page with filter by user/date/module | 8 | Frontend | To Do |
| FE-007 | Export buttons (PDF / Excel) on audit trail viewer | 3 | Frontend | To Do |
| FE-008 | CAPA Effectiveness Review dialog — criteria entry + evidence upload | 5 | Frontend | To Do |

## SPRINT 4 (v0.6) — Hardening, Testing, v0.6 Release

Sprint Goal: Integration testing, bug fixes, documentation, and v0.6 release candidate.

Total story points: 35

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-015 | Full integration test suite for audits/ app (80% coverage) | 8 | Backend | To Do |
| BE-016 | Fix any audit trail gaps found in 21 CFR Part 11 review | 5 | Backend | To Do |
| FE-009 | Responsive layout fixes for audit and CAPA pages | 3 | Frontend | To Do |
| FE-010 | Add loading states and empty states to all new pages | 3 | Frontend | To Do |
| QA-003 | End-to-end testing: create audit → finding → CAPA → effectiveness → close | 8 | QA | To Do |
| DOC-001 | Update API documentation (drf-spectacular / Swagger) | 3 | Backend | To Do |
| DOC-002 | Write user guide for Audit Management module | 3 | QA | To Do |
| REL-001 | v0.6 release — tag, changelog, Docker image push | 2 | DevOps | To Do |

## SPRINT 5 (v0.7) — Complaint Handling Backend

Sprint Goal: Full complaint intake, triage, investigation workflow with regulatory deadline tracking.

Total story points: 42

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-017 | complaints/ app: Complaint, Investigation, MDRReport models | 8 | Backend | To Do |
| BE-018 | ComplaintViewSet with intake form API, batch/lot validation | 5 | Backend | To Do |
| BE-019 | 30/45-day regulatory deadline auto-calculation on complaint creation | 5 | Backend | To Do |
| BE-020 | Celery task: daily check for overdue complaints → email alert | 5 | Backend | To Do |
| BE-021 | MDR flag endpoint — mark complaint for regulatory reporting | 3 | Backend | To Do |
| FE-011 | ComplaintList page with urgency highlighting (overdue = red) | 5 | Frontend | To Do |
| FE-012 | ComplaintForm: multi-step intake (product → complainant → description) | 8 | Frontend | To Do |
| QA-004 | Complaint intake and classification test cases | 3 | QA | To Do |

## SPRINT 6 (v0.7) — OOS/OOT Investigation

Sprint Goal: Two-phase OOS investigation workflow triggered from test result entry.

Total story points: 44

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-022 | OOSInvestigation model with Phase I / Phase II sub-records | 8 | Backend | To Do |
| BE-023 | OOT limit configuration master (3-sigma + custom per product/test) | 5 | Backend | To Do |
| BE-024 | Auto-trigger OOS record on result entry outside spec limits | 5 | Backend | To Do |
| BE-025 | Invalidation workflow with mandatory assignable cause documentation | 5 | Backend | To Do |
| FE-013 | OOS Investigation form: Phase I checklist + analyst retest entry | 8 | Frontend | To Do |
| FE-014 | OOT trend chart: result history + trend line + OOT limit overlay | 5 | Frontend | To Do |
| FE-015 | OOS dashboard KPI: open OOS count, OOS rate by product | 3 | Frontend | To Do |
| QA-005 | OOS Phase I and Phase II test script execution | 5 | QA | To Do |

## SPRINT 7 (v0.7) — Nonconformance Management

Sprint Goal: Complete NC module with disposition workflow, hold management, and batch yield tracking.

Total story points: 44

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-026 | nonconformance/ app: NCReport, Disposition, HoldRecord models | 8 | Backend | To Do |
| BE-027 | Disposition workflow: Use-As-Is/Rework/Reject/RTV with e-signature | 5 | Backend | To Do |
| BE-028 | Batch yield impact calculation: rejected qty / total batch qty | 3 | Backend | To Do |
| BE-029 | NC repeat detection: flag if same product/defect in last 6 months | 5 | Backend | To Do |
| FE-016 | NCForm: batch/lot picker, defect description, quantity affected | 8 | Frontend | To Do |
| FE-017 | Disposition decision dialog with e-signature requirement | 5 | Frontend | To Do |
| FE-018 | NC trend chart: failure modes by product family / time period | 5 | Frontend | To Do |
| QA-006 | NC creation → disposition → CAPA linkage test execution | 5 | QA | To Do |

## SPRINT 8 (v0.7) — Integration & v0.7 Release

Sprint Goal: Cross-module linking (Complaint→NC→CAPA), integration tests, v0.7 release.

Total story points: 36

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-030 | Cross-module linking API: Complaint ↔ NC ↔ Deviation ↔ CAPA | 8 | Backend | To Do |
| BE-031 | Related records panel: show all linked records on any quality event | 5 | Backend | To Do |
| FE-019 | Related Records component — renders linked items as chips with links | 5 | Frontend | To Do |
| QA-007 | End-to-end: Complaint → Investigation → NC → CAPA → Close | 8 | QA | To Do |
| QA-008 | Regression test suite — run all S1–S7 test cases | 5 | QA | To Do |
| REL-002 | v0.7 release — tag, changelog, deploy to staging | 2 | DevOps | To Do |
| SEC-001 | Dependency audit (pip-audit + npm audit) | 3 | DevOps | To Do |

## SPRINT 9 (v0.8) — Risk Management

Sprint Goal: Risk register, FMEA scoring, risk matrix visualization, mitigation tracking.

Total story points: 42

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-032 | risk/ app: Risk, FMEAItem, Mitigation, ResidualRisk models | 8 | Backend | To Do |
| BE-033 | RPN auto-calculation: Severity × Occurrence × Detection | 3 | Backend | To Do |
| BE-034 | Risk-to-CAPA linkage; risk status update on CAPA closure | 5 | Backend | To Do |
| FE-020 | Risk Register table with filterable RPN, owner, status columns | 5 | Frontend | To Do |
| FE-021 | FMEA entry form with inline RPN calculator | 5 | Frontend | To Do |
| FE-022 | 5×5 Risk Matrix heat map (D3 or Chart.js) | 8 | Frontend | To Do |
| FE-023 | Mitigation tracking panel per risk item | 3 | Frontend | To Do |
| QA-009 | Risk creation → FMEA scoring → mitigation → residual risk test | 5 | QA | To Do |

## SPRINT 10–12 (v0.8) — Supplier Quality Management

Sprint Goal: Full SQM including supplier master, qualification workflow, ASL, and scorecard.

Total story points: 72

| Ticket ID | User Story | SP | Layer | Status |
| --- | --- | --- | --- | --- |
| BE-035 | suppliers/ app: Supplier, QualificationRecord, ASLEntry, Scorecard, SCN models | 13 | Backend | To Do |
| BE-036 | Qualification workflow with document checklist and approval gate | 8 | Backend | To Do |
| BE-037 | ASL versioning — locked, approved, expiry-date-tracked list | 8 | Backend | To Do |
| BE-038 | Scorecard auto-calculation from delivery + quality + responsiveness | 5 | Backend | To Do |
| BE-039 | SCN intake and internal review workflow | 5 | Backend | To Do |
| BE-040 | Celery task: alert 30 days before qualification expiry | 3 | Backend | To Do |
| FE-024 | Supplier directory page with qualification status badges | 5 | Frontend | To Do |
| FE-025 | Qualification wizard: 4-step form (profile → docs → audit → approval) | 8 | Frontend | To Do |
| FE-026 | ASL page — locked list view + version history | 5 | Frontend | To Do |
| FE-027 | Scorecard dashboard: radar chart per supplier | 5 | Frontend | To Do |
| QA-010 | Supplier qualification and ASL approval end-to-end test | 5 | QA | To Do |
| REL-003 | v0.8 release — all Phase 1 modules complete | 2 | DevOps | To Do |

# Definition of Done (DoD)

Every story must meet ALL of the following criteria before being marked Done:

| Category | Criteria |
| --- | --- |
| Code | Code reviewed and approved by at least one peer |
| Code | No new lint errors (flake8 backend, ESLint frontend) |
| Code | No new TypeScript errors (strict mode) |
| Testing | Unit test coverage ≥ 80% for new backend code |
| Testing | All existing tests still passing (no regressions) |
| Testing | QA test cases executed and passed |
| Security | No new high/critical vulnerabilities in dependency audit |
| Compliance | E-signature enforced on all required status transitions |
| Compliance | Audit trail records created for all data changes |
| Compliance | No hard delete of any regulated record |
| Documentation | API endpoint documented in Swagger/OpenAPI spec |
| Documentation | User-facing changes noted in changelog |
| Deployment | Feature deployed to staging environment |
| Accessibility | No new WCAG 2.1 Level AA violations |